## Week1
Weekly Task | Hours
Meeting with Analytics capstone coordinator | 1
Meeting with standard capstone coordinators | 1
Writing mails to client | 1
Connecting Client on Riipen portal and accessing project related documents | 1
Understanding business requirement and throughly going through all the files | 4
Group discussion with the team and designing the project timeline | 10
Waiting for clients approval and their response | 15
Total hours | 33

## Week2
Weekly Task | Hours
Meeting with capstone coordinator (Sidney) and assigned to new project | 2
Meeting with standard capstone coordinators | 1
Writing mails to client | 1
Connecting Client on Riipen portal | 0.5
Requesting client for a meeting and all the project related documents | 1
Understanding business requirement and throughly going through all the files | 4
Group discussion with the team and designing the project timeline | 12
Preparing project proposal and exploring technical aspects required to achive tasks | 12
Total hours | 33.5

## Week3
Weekly Task | Hours
Meeting with capstone coordinator (Sidney) | 1
Meeting with standard capstone coordinators | 1.5
Setting up environment on AWS | 2
Team meeting to discuss the road map of the project | 3
Creating frontend part of the project and used git for version control | 2
Dividing project among other team members and assigning them tasks | 3
Exploring and learing how to different AWS services | 20
Total hours | 32.5

## Week4
Weekly Task | Hours
Meeting with capstone coordinator (Sidney) | 1
Meeting with standard capstone coordinators | 1.5
Understanding AWS cognito and how to use it to authorize guest users | 3
Meeting with client and discuss project proposal with other potential service providers | 1
Understanding the conept of AWS amplify and how to leverage its features in our development | 6
Created user pool in Cognito to save guest users profiles | 4
Created sample React project implimenting authentication and authorization using AWS cognito | 16
Total hours | 32.5