## Week1
Weekly Task | Hours
Meeting with Analytics capstone coordinator | 1
Meeting with standard capstone coordinators | 1
Writing mails to client | 1
Connecting Client on Riipen portal and accessing project related documents | 1
Understanding business requirement and throughly going through all the files | 4
Group discussion with the team and designing the project timeline | 10
Waiting for clients approval and their response | 15
Total hours | 33

## Week2
Weekly Task | Hours
Meeting with capstone coordinator (Sidney) and assigned to new project | 2
Meeting with standard capstone coordinators | 1
Writing mails to client | 1
Connecting Client on Riipen portal | 0.5
Requesting client for a meeting and all the project related documents | 1
Understanding business requirement and throughly going through all the files | 4
Group discussion with the team and designing the project timeline | 12
Preparing project proposal and exploring technical aspects required to achive tasks | 12
Total hours | 33.5